## Old RMS
Screen/Function | Feature | Sub Feature | User Role1 | User Role2 | .. | Description | Planned-In | In Charge | Done-In | RDS | Status | Updated | Update Details
Home Page | Common |  | x | x | x | Show sliders, hot posts, featured products + the sider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking - Shown product information includes its thumbnail, title, brief information; the user is redirected to the product's details on his/her clicking | Not Yet | Mạnh | Not Yet |  |  | Not Yet
Blogs List | Common |  |  |  |  | Show the posts paginatedly (sorted by updated date, paginated) + the sider with the post search box, post categories, the latest posts, and static contacts/links; Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking | Not Yet |  |  |  |  | Not Yet
Blog Details | Common |  |  |  |  | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, post categories, static contacts/links | Not Yet |  |  |  |  | Not Yet
Products List | Common |  |  |  |  | Show the products paginatedly (sorted by updated date) + the sider with the product search box, product categories, the latest products, and static contacts/links; - Shown product information includes its thumbnail, title, brief information, original price, and sale price; - The user is redirected to the product's details on his/her clicking on the product - The user can choose to add the product to the cart or to feedback on the product by clicking the product's Buy & Feedback buttons responsively | Iteration 1 | Dũng |  |  |  | Not Yet
Product Details | Common |  |  |  |  | Show product details (including title, category, images, original price, sale price, and product details) + the sider with the product search box, product categories, the latest products, and static contacts/links | Iteration 1 | Dũng |  |  |  | Not Yet
Cart Details | Common |  |  |  |  | Show the cart details with list of the user's chosen products (including Id, title, price, quantity, total cost) and the total order price + the sider with the product search box, product categories, the latest products, and static contacts/links; The user can - Change the quantity of each product: the total cost is automatically adjusted - Choose to delete/remove product by clicking on the deleting icon - Click the Choose More Product button to go to Products List page - Click the Check Out button to go to the Cart Contact page Please notes: the user's chosen products from the last browsing session are remained in his/her cart until s/he submit the cart. However, the product prices are updated with the latest prices in the system | Not Yet |  |  |  |  | Not Yet
Cart Contact | Common |  |  |  |  | Show the list of user chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, gender, email, mobile, address, notes) for user to edit/input + the sider with the product search box, product categories, the latest products, and static contacts/links - In case the user has logged in, the receiver information would be filled with the user's information - The user can click the Change button to come back to the Cart Details page for changing the choosing products, click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product) | Not Yet |  |  |  |  | Not Yet
Cart Completion | Blog/Share | Public Blogs |  |  |  | This page show the cart completion notes + the sider with the product search box, product categories, the latest products, and static contacts/links; Before this page is shown: - The Order status is changed to submitted; - The product's available quantities are updated accordingly - The submitted order is assigned automatically to the active salers rotatedly - If the receiver information (name, email, mobile, gender) is new or changed (checking via the email0, the latest receiver information is stored in the system as latest & historical system contact information (for the marketing's reference later) - The customer/user would be received the order confirmation & payment guides via his/her email. Those information is shown on the page also. The payment information (banking account,...) are taken from the system configuration file | Iteration 2 |  |  |  |  | Not Yet
Feedback | Blog/Share | Public Blogs |  |  |  | On receiving the bought products successfully, the receiver would receive a confirmation email with the guides to feedback on each of the received product; Beside, the user/receive could also give the feedback (on a specific product or general feedback) via the website; The user also call this screen from the system menu on the header; The feedback information includes contact information (full name, gender, email, mobile), rated star, the attached images and the contact's free-format feedback The page sider is also shown with the product search box, product categories, static contacts/links; | Iteration 2 |  |  |  |  | Not Yet
User Login | Blog/Share | Post Management |  |  |  | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it | Iteration 1 | Mạnh | Not Yet |  | Doing | Not Yet
User Register | Blog/Share | Post Management |  |  |  | This is a pop-up screen which allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile, and address; User then need to verify by clicking the link sent via email to him/her before being able to access the system | Iteration 1 | Mạnh |  |  | Doing | Not Yet
Reset Password | System Admin | System Setting |  |  |  | The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. | Iteration 1 | Mạnh |  |  |  | Not Yet
Change Password | System Admin | System Setting |  |  |  | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) | Iteration 1 | Mạnh |  |  |  | Not Yet
User Profile | System Admin | User Management |  |  |  | This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. Please note that s/he is not allowed to change the email | Iteration 1 | Mạnh |  |  |  | Not Yet
User Authorization | System Admin | User Management |  |  |  | Implementation of authorization mechanism in the system, including the specify the role of logged-in user, his/her authorized page links (building the displayed menu items (in the front end) and preventing unauthorized access via enter the links directly) | Iteration 1 | Mạnh |  |  |  | Not Yet
My Orders | [5 empty] | Show the list of user's orders paginatedly + the sider with the product search box, product categories, the latest products, and static contacts/links - Each order include below information: id, ordered date, product (first product name & number of other products if any), total cost, status; - On clicking the link under the order id, user would be redirected to the Order Information page | Iteration 2 | Vũ |  |  |  | Not Yet
Order Information | [5 empty] | Show the order details, including the information as below + the sider with the product search box, product categories, the latest products, and static contacts/links - The order id, order date, total cost, status - The receiver information: full name, gendar, email, mobile - This list of ordered products, each product include following information & the links/buttons that allow the user to re-buy or feedback: thumbnail, name, category, unit price, quantity, total cost For the submitted orders, the user can choose to update (redirect the user to the Cart Details page for that) or cancel the order | Iteration 2 | Vũ |  |  |  | Not Yet
MKT Dashboard | [5 empty] | Show statistics of posts, products, customers, feedbacks & the trend of new customers by day for the last 7 days (the start date & end date can be adjustable) | Iteration 2 | Mạnh |  |  |  | Not Yet
Posts List | [5 empty] | Show the paginated list of posts (include posts' id, thumbnail, title, category, author, featured, and status information): - The user can filter the post by category, author, status or search by title - Sortable by title, category, author, featured, or status - From each post, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new post | Iteration 1 | Thái |  |  |  | Not Yet
Post Details | [5 empty] | Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | Iteration 1 | Thái |  |  |  | Not Yet
Sliders List | [5 empty] | Show the paginated list of sliders (including sliders' id, title, image, backlink, status) - The user can filter the sliders by the status + search by title or backlink - For each slider, the user can choose to hide, show, edit it | Iteration 3 |  |  |  |  | Not Yet
Slider Details | [5 empty] | Show detailed slider information (image, title, backlink, status, notes) | Iteration 3 |  |  |  |  | Not Yet
Products List | [5 empty] | Show the paginated list of products (include products' id, thumbnail, title, category, list price, sale price, featured, and status information): - The user can filter the product by category, status or search by title, brief info - Sortable by title, category, list price, sale price, featured, or status - From each product, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new product | Iteration 2 | Dũng |  |  |  | Not Yet
Product Details | [5 empty] | Show detailed product information (thumbnail, category, title, brief information, attached images, description, quantity, list price, sale price, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | Iteration 2 | Dũng |  |  |  | Not Yet
Customers List | [5 empty] | Show the list of customers / contacts paginatedly (include contacts' id, full name, gender, email, mobile, status): - The user can filter the customers by status + search by full name, email, mobile - Sortable by full name, email, mobile, status - From each customer, the user can choose to add new, view or edit it | Iteration 1 | Long |  |  |  | Not Yet
Customer Details | [5 empty] | Show detailed customer/contact information (full name, gender, email, mobile, address, status), from that allow the user to input, view or edit them (excep for the status which is generated automatically - contact, potential or customer) Besides, the screen also shows the list of customer/contact changes history in the form of a table which includes following columns: email, full-name, gender, mobile, address, updated by, updated date | Iteration 1 | Long |  |  |  | Not Yet
Feedbacks List | [5 empty] | Show the list of feedbacks paginatedly (include feedbacks' contact full name, product name, rated star, status): - The user can filter the feedbacks by status, product, rated star + search by full name, feedback content - Sortable by full name, product name, rated star, status - From each feedback, the user can choose to view or change it's status | Iteration 2 |  |  |  |  | Not Yet
Feedback Details | [5 empty] | Show the feedback details (contact full name, email, mobile, product, rated star, feedback, images status) from that allow the user to change its status | Iteration 2 |  |  |  |  | Not Yet
Sale Dashboard | [5 empty] | Show the trend of success/total orders, and the revenues trends by day for the last 7 days for all or a specific sale person (the start date, end date, sale, order status can be adjustable) | Iteration 2 | Mạnh |  |  |  | Not Yet
Orders List |  |  | f |  |  | Show the list of orders paginatedly - The list can be shorted by the order date, customer name, total cost, status - Each order include below information: id, ordered date, customer name, product (first product name & number of other products if any), total cost, status; - Allow the users to filter the order by the order date (from, to), sale name, status - Allow the user to search the orders by order id, customer name - On clicking the link under the order id, user would be redirected to the Order Details page | Iteration 1 | Vũ |  |  |  | Not Yet
Order Details | [5 empty] | Show the order details, including the following information: - Basic order information: order id, customer full name, email, mobile, order date, total cost, sale name, status - The receiver information: full name, gendar, email, mobile, address - This list of ordered products, each product include following information: thumbnail, name, category, unit price, quantity, total cost Sale Manager & the assigned Sale can change the order status & the sale notes Sale Manager can assign the order to other sale | Iteration 1 | Vũ |  |  |  | Not Yet
Admin Dashboard | [5 empty] | Show statistics of new orders (success, cancelled, submitted), revenues (total, by product categories), customers (newly registered, newly bought), feedbacks (average star: total, by product categories) & the trend of order counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) | Iteration 2 | Mạnh |  |  |  | Not Yet
Users List | [5 empty] | Show the paginated list of registered users (include users' id, full name, gender, email, mobile, role, status): - The admin can filter the users by gender, role, status - Allow the admin to seach users by full name, email, mobile - The list is sortable by id, fullname, gender, email, mobile, role, status - From each user, the admin can choose to view or edit it - The page also have the button/link that allows the admin to add new user | Iteration 2 | Thái |  |  |  | Not Yet
User Details | [5 empty] | Show detailed user information (avatar, full name, gender, email, mobile, role, address, status), from that allow the user to add new, view or edit user information - After adding, new generated login password would be email to the new user - The admin can only edit/update the role and status of the user | Iteration 2 | Thái |  |  |  | Not Yet
Settings List | [5 empty] | Show the paginated list of settings (include settings' id, type, value, order, status): - The admin can filter the setting by type, status - Allow the admin to seach settings by value - The list is sortable by id, type, value, order, status - From each setting, the admin can choose to view, activate/deactivate, or edit it - The page also have the button/link that allows the admin to add new setting | Iteration 2 |  |  |  |  | Not Yet
Setting Details | [5 empty] | Show detailed user information (type, value, order, description, status), from that allow the user to add new, view or edit setting information | Iteration 2 |  |  |  |  | Not Yet
Delivery List | [6 empty] | Iteration 2 |  |  |  |  | Not Yet
Delivery Detail | [6 empty] | Iteration 2 |  |  |  |  | Not Yet

## New RMS
Screen/Function | QA | Feature | Sub Feature | LOC | Guest | Customer | MKT | Sale | Shipper | Admin | In Charge | Status | Done | Notes | RDS | Updated | Update Details
Home Page |  | Common |  | 120 | x | x | x | x | x |  | Mạnh | To Do | Not Yet |  |  | Not Yet
Blogs List |  | Common |  | 60 | x | x | x | x | x |  |  | To Do | Not Yet |  |  | Not Yet
Blog Details |  | Common |  | 60 |  | x | x | x | x |  |  | To Do | Not Yet |  |  | Not Yet
Products List |  | Common |  | 240 | x | x | x | x | x |  | Dũng | Doing | Not Yet |  |  | Not Yet
Product Details |  | Common |  | 120 |  | x | x | x | x |  | Dũng | To Do | Not Yet |  |  | Not Yet
Cart Details | x |  |  | 120 |  |  |  | x |  |  |  | To Do | Not Yet |  |  | Not Yet
Cart Contact | x |  |  | 120 |  |  |  | x |  |  |  | To Do | Not Yet |  |  | Not Yet
Cart Completion | x |  |  | 240 |  |  |  | x |  |  |  | To Do | Not Yet |  |  | Not Yet
Feedback |  |  |  | 60 |  | x | x | x | x |  |  | To Do | Not Yet |  |  | Not Yet
User Login |  |  |  | 60 | x | x | x | x | x |  | Mạnh | Doing | Not Yet |  |  | Not Yet
User Register |  |  |  | 60 | x | x | x | x | x |  | Mạnh | Doing | Not Yet |  |  | Not Yet
Reset Password |  |  |  | 120 |  | x | x | x | x |  | Mạnh | To Do | Not Yet |  |  | Not Yet
Change Password |  |  |  | 60 |  | x | x | x | x |  | Mạnh | To Do | Not Yet |  |  | Not Yet
User Profile |  |  |  | 60 |  | x | x | x | x |  | Mạnh | Doing | Not Yet |  |  | Not Yet
User Authorization |  |  |  | 240 | [6 empty] | Mạnh | To Do | Not Yet |  |  | Not Yet
My Orders | x |  |  | 60 |  |  |  | x |  |  | Vũ | To Do | Not Yet |  |  | Not Yet
Order Information | x |  |  | 120 |  |  |  | x |  |  | Vũ | To Do | Not Yet |  |  | Not Yet
MKT Dashboard |  |  |  | 120 |  | x |  |  |  |  | Mạnh | To Do | Not Yet |  |  | Not Yet
Posts List |  |  |  | 120 |  | x |  |  |  |  | Thái | Doing | Not Yet |  |  | Not Yet
Post Details |  |  |  | 60 |  | x |  |  |  |  | Thái | Doing | Not Yet |  |  | Not Yet
Sliders List |  |  |  | 60 |  | x | [5 empty] | To Do | Not Yet |  |  | Not Yet
Slider Details |  |  |  | 120 |  | x | [5 empty] | To Do | Not Yet |  |  | Not Yet
Products List |  |  |  | 120 |  | x |  |  |  |  | Dũng | To Do | Not Yet |  |  | Not Yet
Product Details |  |  |  | 60 |  | x |  |  |  |  | Dũng | To Do | Not Yet |  |  | Not Yet
Customers List |  |  |  | 60 |  | x |  |  |  |  | Long | To Do | Not Yet |  |  | Not Yet
Customer Details |  |  |  | 120 |  | x |  |  |  |  | Long | To Do | Not Yet |  |  | Not Yet
Feedbacks List |  |  |  | 120 |  | x | [5 empty] | To Do | Not Yet |  |  | Not Yet
Feedback Details | x |  |  | 60 |  |  | x |  |  |  |  | To Do | Not Yet |  |  | Not Yet
Sale Dashboard | x |  |  | 60 |  |  | x |  |  |  | Mạnh | To Do | Not Yet |  |  | Not Yet
Orders List | x |  |  | 120 |  |  | x | x |  |  | Vũ | To Do | Not Yet |  |  | Not Yet
Order Details |  |  |  | 60 |  |  |  |  | x |  | Vũ | To Do | Not Yet |  |  | Not Yet
Admin Dashboard |  |  |  | 60 |  |  |  |  | x |  | Mạnh | To Do | Not Yet |  |  | Not Yet
Users List |  |  |  | 60 |  |  |  |  | x |  | Thái | To Do | Not Yet |  |  | Not Yet
User Details |  |  |  | 60 |  |  |  |  | x |  | Thái | To Do | Not Yet |  |  | Not Yet
Settings List |  |  |  | 60 |  |  |  |  | x |  |  | To Do | Not Yet |  |  | Not Yet
Setting Details |  |  |  | 120
Delivery List |  |  |  | 60
Delivery Detail |  |  |  | 60

## Interation 1
No | Screen/Function | LOC | Level | In Charge | Status | Progress (%) | Plan Start Date | Plan Complete Date | Actual Start | Actual Complete | Notes
1 | User Login | 60 | Simple | ManhNH | Done | 100% | 2025-01-16 | 2025-01-20 | 2025-01-16 | 2025-02-01
| BE |  |  |  | Done | 100%
| FE |  |  |  | Done | 100%
| Doc |  |  |  | Done | 100%
2 | User Register | 60 | Simple | ManhNH | Done | 100% | 2025-01-16 | 2025-01-25 | 2025-01-20 | 2025-02-07
| BE |  |  |  | Done | 100%
| FE |  |  |  | Done | 100%
| Doc |  |  |  | Done | 100%
3 | Reset Password | 120 | Simple | ManhNH | Doing | 0% | 2025-01-16 |  | 2025-02-03
| BE |  |  |  | Doing | 30%
| FE |  |  |  | Doing | 90%
| Doc |  |  |  | Doing | 0%
4 | Change Password | 60 | Simple | ManhNH | Doing | 0% | 2025-01-16 |  | 2025-02-03
| BE |  |  |  | Doing | 10%
| FE |  |  |  | Doing | 0%
| Doc |  |  |  | Doing | 0%
5 | User Profile | 60 | Simple | ManhNH | Doing | 0% | 2025-01-16 | 2025-02-20
| BE |  |  |  | Doing | 0%
| FE |  |  |  | Doing | 0%
| Doc |  |  |  | Doing | 0%
6 | User Authenication | 240 | Simple | ManhNH | Doing | 0% | 2025-01-16 |  | 2025-02-08
| BE |  |  |  | Doing | 0%
| FE |  |  |  | Doing | 90%
| Doc |  |  |  | Doing | 0%
8 | Post List | 120 | Simple | ThaiQT | Doing | 90% | 2025-01-17 | 2025-02-08 | 2025-01-17 | 2025-02-09
| BE |  |  |  | Done | 100%
| FE |  |  |  | Done | 100%
| Doc |  |  |  | Doing | 0%
9 | Post Detail | 120 | Simple | ThaiQT | Doing | 85% | 2025-01-17 | 2025-02-08 | 2025-01-17 | 2025-02-09
| BE |  |  |  | Done | 100%
| FE |  |  |  | Doing | 80%
| Doc |  |  |  | Done | 100%
10 | Customer List | 60 |  | Long | Doing | 0%
[5 empty] | Doing | 0%
[5 empty] | Doing | 0%
[5 empty] | Doing | 0%
11 | Customer Detail | 60 |  | Long | Doing | 0%
[5 empty] | Doing | 0%
[5 empty] | Doing | 0%
[5 empty] | Doing | 0%
12 | Order List | 60 |  | Vu | Doing | 50% | 2025-01-23
[5 empty] | Doing | 0%
[5 empty] | Doing | 0%
[5 empty] | Doing | 0%
13 | Order Detail | 60 |  | Vu | Doing | 0%
[5 empty] | Doing | 0%
[5 empty] | Doing | 0%
[5 empty] | Doing | 0%
14 | Product List | 120 | Medium | DungPT | Done | 100% | 2025-01-20 | 2025-02-08 | 2025-01-25 | 2025-02-21
| FE |  |  |  | Done | 100%
| BE |  |  |  | Done | 100%
| Doc |  |  |  | Done | 100%
15 | Product Detail | 120 | Medium | DungPT | Done | 100% | 2025-01-20 | 2025-02-08 | 2025-01-25 | 2025-02-21
| FE |  |  |  | Done | 100%
| BE |  |  |  | Done | 100%
| Doc |  |  |  | Done | 100%
16 | Cart Detail | 120 | Simple | Vu | Done | 100% | 2025-01-17 | 2025-02-08 | 2025-01-23 | 2025-02-08
| BE |  |  |  | Done | 100%
| FE |  |  |  | Done | 100%
| Doc |  |  |  | Done | 100%
17 | View Cart | 120 | Simple | Vu | Doing | 80% | 2025-01-17 | 2025-02-08 | 2025-01-23 | 2025-02-08
| BE |  |  |  | Doing | 80%
| FE |  |  |  | Doing | 100%
| Doc |  |  |  | Doing | 70%

## Interation 2
No | Screen/Function | LOC | Level | In Charge | Status | Progress (%) | Plan Start Date | Plan Complete Date | Actual Start | Actual Complete | Notes
1 | Home | 120 | Simple | ManhNH | Done | 100% | 2025-02-11 | 2025-02-15 | 2025-02-11 | 2025-02-16
| BE |  |  |  |  | 100%
| FE |  |  |  |  | 100%
| Doc |  |  |  |  | 100% | [6 empty] | Total LOC
3 | Order List | 60 | Simple | DungPT | Done |  | 2025-02-11 | 2025-03-03 | 2025-02-20 | 2025-03-04 |  | Vu | 480
| BE |  |  |  |  | 100%
| FE |  |  |  |  | 100%
Doc
4 | Order Detail | 60 | Simple | DungPT | Done |  | 2025-02-11 | 2025-03-03 | 2025-02-22 | 2025-03-04
| BE |  |  |  |  | 100%
| FE |  |  |  |  | 100%
Doc
7 | Order Information | 120 | Medium | DungPT | Done |  | 2025-02-11 | 2025-03-03 | 2025-02-22 | 2025-03-04
| BE |  |  |  |  | 100%
| FE |  |  |  |  | 100%
Doc
8 | My Order | 60 | Simple | DungPT | Done |  | 2025-02-11 | 2025-03-03 | 2025-02-22 | 2025-03-04
| BE |  |  |  |  | 100%
| FE |  |  |  |  | 100%
Doc
9 | User Authenication | 240 | Complex | ManhNH | Done |  | 2025-02-11 | 2025-03-03 | 2025-02-11 | 2025-03-03
| BE |  |  |  |  | 100%
| FE |  |  |  |  | 100%
Doc
10 | Customer List | 60 | Simple | DungPT | Done |  | 2025-02-12 | 2025-03-03 | 2025-02-22
| BE |  |  |  |  | 100%
| FE |  |  |  |  | 100%
Doc
13 | Blog List | 60 | Simple | Long |  |  | 2025-02-12 | 2025-03-03
BE
FE
Doc
14 | Blog Detail | 60 | Simple | Long |  |  | 2025-02-12 | 2025-03-03
BE
FE
Doc
15 | Cart Contact | 120 | Medium | Vu | Done | 100% | 2025-02-13 | 2025-03-03 | 2025-02-20 | 2025-03-02
BE
FE
Doc
16 | Cart completion | 240 | Complex | Vu | Done |  | 2025-02-13 | 2025-03-03 | 2025-02-13 | 2025-03-04
| BE |  |  |  |  | 100%
FE
Doc
Interation 1
No | Screen/Function | LOC | Level | In Charge | Status | Progress (%) | Plan Start Date | Plan Complete Date | Actual Start | Actual Complete | Notes
1 | View Cart | 120 | Simple | Vu | Done | 100% | 2025-01-17 | 2025-02-08 | 2025-01-23 | 2025-02-08
| BE |  |  |  |  | 100%
| FE |  |  |  |  | 100%
| Doc |  |  |  |  | 100%

## Interation 3
No | Screen/Function | LOC | Level | In Charge | Status | Progress (%) | Plan Start Date | Plan Complete Date | Actual Start | Actual Complete | Notes
1 | MKT Dashboard | 60 | Simple | Vu | Done |  | 2025-03-10 | 2025-03-23
| BE |  |  |  |  | 100%
FE
| Docs | [11 empty] | Total LOC
2 | Customer Details | 60 | Simple | DungPT | Done | 100% | 2025-03-10 | 2025-03-23 |  | 2025-03-23 |  | ManhNH | 180
| BE | [9 empty] | Mạnh code
FE
Docs
3 | Sale Dashboard | 60 | Simple | Vu | Done | 100% | 2025-03-10 | 2025-03-23 | 2025-03-10 | 2025-03-20
BE
FE
Docs
4 | Settings List | 60 | Simple | DungPT | Doing | 30% | 2025-03-10 | 2025-03-23
BE
FE
Docs
5 | Setting Details | 60 | Simple | DungPT | Doing | 30% | 2025-03-10 | 2025-03-23
BE
FE
Docs
6 | User Details | 60 | Simple | DungPT | Done | 100% | 2025-03-10 | 2025-03-23 |  | 2025-03-23
| BE | [9 empty] | Mạnh code
FE
Docs
7 | Reset Password | 120 | Medium | ManhNH | Done | 100% | 2025-03-10 | 2025-03-23 | 2025-03-10 | 2025-03-12
BE
FE
Docs
8 | Change password | 60 | Simple | ManhNH | Done | 100% | 2025-03-10 | 2025-03-23 | 2025-03-10 | 2025-03-19
BE
FE
Docs
Interation 1
No | Screen/Function | LOC | Level | In Charge | Status | Progress (%) | Plan Start Date | Plan Complete Date | Actual Start | Actual Complete | Notes
| Cart Completion |  | Complex | Vu | Done

## Reference
Item | Failed | Normal Cases |  |  | Best Case | Notes
No of screens/functions | 4 | 5 | 6 | 7 | 8 | Tổng số screens/functions hoàn thiện đủ happy cases
Maximum LOC (C) | 480 | 600 | 720 | 840 | 960 | Số LOC quy đổi (L2-3-4 = 33%, 33%, 33%)
Quality Level (Q) | 50% | 50% | 75% | 75% | 75% | Chất lượng màn hình/chức năng**
Evaluated LOC | 240 | 300 | 540 | 630 | 720 | Số LOC đạt được (LOC = C*Q)
LOC Grade (LG) | 3.6364 | 4.5455 | 8.1818 | 9.5455 | 10.9091 | 70% | Tỷ trọng điểm LOC
Non-LOC Grade (Pkg) | 6 | 6 | 7 | 7 | 8 | 30% | Tỷ trọng điểm quy trình, material liên quan.. Riêng iter3 thì tỷ trọng này là 40%
ĐIỂM ĐÁNH GIÁ (/10) | 4.3455 | 4.9818 | 7.8273 | 8.7818 | 10.0364
Converted LOC (for each of the complexity levels)
Complexity Level | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | Level 7 | Level | Fields | Trans* | LOC | Notes
Converted LOC | 60 | 90 | 120 | 150 | 180 | 210 | 240 | Level 1 | 3-5 | 2 | 60 | 3-5 fields OR 2 trans
[8 empty] | Level 2 | 6-7 | 3 | 90 | 6-7 fields OR 3 trans
Screen/Function Complexity Levels | [7 empty] | Level 3 | 8-9 | 4 | 120 | 8-9 fields OR 4 trans
Screen complexity can be defined based on the screen's fields OR screen/function's transactions | [7 empty] | Level 4 | 10-11 | 5 | 150 | 10-11 fields OR 5 trans
- Transactions can be counted as number of transactions to the database or external systems/subsystems | [7 empty] | Level 5 | 12-13 | 6 | 180 | 12-13 fields OR 6 trans
- Fields are screen's actionable components or database table fields; if there are some transactions those are | [7 empty] | Level 6 | 14-15 | 7 | 210 | 14-15 fields OR 7 trans
not "related" to any fields, each of those transactions are counted as two fields and add those extra number | [7 empty] | Level 7 | >15 | >7 | 240 | >15 fields OR >7 trans
to the total number of fields to define the screen/function complexity | [7 empty] | *One trans (transactions) = Two fields (actionable screen components)
Complexity Level | Level 1 | Level 2 | Level 3 | Level 4 | Level 5 | Level 6 | Level 7
No of transactions (to database, external,..) | 2 | 3 | 4 | 5 | 6 | 7 | >7
One transaction can be converted as two actionable fields
OR: no of fields | 3-5 | 6-7 | 8-9 | 10-11 | 12-13 | 14-15 | >15
Screen/Function Quality Levels & LOC Evaluation Rate
Level | One transaction can be converted as two actionable fields 3-5: Rate; One transaction can be converted as two actionable fields 6-7: Notes
L1_Happy Cases | One transaction can be converted as two actionable fields 3-5: 50%; One transaction can be converted as two actionable fields 6-7: The screen/function is workable, all happy cases are included
L2_All Cases | One transaction can be converted as two actionable fields 3-5: 75%; One transaction can be converted as two actionable fields 6-7: The screen/function is workable with both happy and unhappy cases included
L3_Optimized | One transaction can be converted as two actionable fields 3-5: 100%; One transaction can be converted as two actionable fields 6-7: All happy & unhappy cases included + the function/screen is optimized in term of UX and and business logics (suitability to real-world use cases)
Some samples of screen complexity defining are as following
Sample #1 | [7 empty] | Sample #2
Sample #3